## Sheet1
Category	Issue	Type	Completed
character sheet	chits not showing up	bug	yes
character sheet	show current character score	feature	no
character sheet	switch between multiple characters	feature	no
character sheet	when selecting chits, grey out unselectable ones	feature	no
combat	action phase: alert weapon	feature	no
combat	action phase: run away	feature	yes
combat	character death	feature	no
combat	dwarf: duck chit	feature	no
combat	end combat when 2 rounds of nothing happens	feature	yes
combat	imp/demon	feature	no
combat	monster head/club	feature	no
combat	select target from square with multiple targets	feature	no
combat	set inspection header to clearing name	feature	no
combat	use horse for maneuver	feature	no
general	activity: follow	feature	no
general	animate clock when going to next phase	feature	no
general	berserker: berserk chit	feature	no
general	end game – score	feature	no
general	fix activity icon sizes for screen	bug	no
general	fix game blocked when no change available when making change for fatigued chits	bug	no
general	fix touch detection missing touches	bug	no
general	handle activity selection/execution for multiple characters	feature	yes
general	new game – clean up unselected characters	feature	partial
general	new game – don't show dwellings before start location selected	feature	no
general	new game – new game while old one is in progress	feature	no
general	new game – select character victory points	feature	no
general	new game – show character equipment and stats	feature	no
general	new game – show/select characters	feature	yes
general	new game – start game	feature	yes
general	options screen – show basic interaction rules	feature	no
general	options screen – show credits	feature	no
general	use own random number generator	feature	yes
items	basic item data on image	feature	no
items	detailed item data view	feature	no
items	item effects	feature	no
magic	animate/cycle magic colors supplied on each clearing	feature	no
magic	enchant chit	feature	no
magic	enchant tile	feature	no
magic	new game – select starting spells	feature	no
magic	setup – initialize magic cards	feature	no
magic	show color magic supplied by day on clock	feature	no
magic	spells	feature	no
map	double-tap on character name centers on character on map	feature	no
map	fix character chit rotation	bug	no
map	game piece stack – sort by size	feature	no
map	inspect clearing pieces	feature	no
map	make hidden paths brown/green instead of black/yellow	feature	yes
map	use pinch zoom to change map size	feature	no
monsters	spawn/regenerate ghosts	feature	no
natives	hire	feature	no
natives	trade	feature	no
save/load	basic functionality	feature	yes
save/load	multiple save files	feature	no
map	if you are in select clearing mode, do not allow changing the activity until a clearing is selected	bug	no