## Sheet1
Category	Issue	Type	Completed	Phase
character sheet	chits not showing up	bug	yes	1
character sheet	show current character score	feature	yes	1
character sheet	switch between multiple characters	feature	yes	1
character sheet	when selecting chits, grey out unselectable ones	feature	yes	1
combat	action phase: alert weapon	feature	yes	1
combat	action phase: run away	feature	yes	1
combat	character death	feature	yes	1
combat	dwarf: duck chit	feature	yes	1
combat	end combat when 2 rounds of nothing happens	feature	yes	1
combat	imp/demon	feature	no	x
combat	monster head/club	feature	no	1
combat	select target from square with multiple targets	feature	yes	1
combat	set inspection header to clearing name	feature	yes	1
combat	use horse for maneuver	feature	no	1
general	activity: follow	feature	no	x
general	animate clock when going to next phase	feature	no	1
general	berserker: berserk chit	feature	mostly	1
general	end game – score	feature	yes	1
general	fix activity icon sizes for screen	bug	yes	1
general	fix game blocked when no change available when making change for fatigued chits	bug	yes	1
general	fix touch detection missing touches	bug	no	1
general	handle activity selection/execution for multiple characters	feature	yes	1
general	new game – clean up unselected characters	feature	partial	1
general	new game – don't show dwellings before start location selected	feature	no	1
general	new game – new game while old one is in progress	feature	no	1
general	new game – select character victory points	feature	yes	1
general	new game – show character equipment and stats	feature	no	1
general	new game – show/select characters	feature	yes	1
general	new game – start game	feature	yes	1
general	options screen – show basic interaction rules	feature	no	1
general	options screen – show credits	feature	no	1
general	use own random number generator	feature	yes	1
items	basic item data on image	feature	no	x
items	detailed item data view	feature	no	x
items	item effects	feature	no	x
magic	animate/cycle magic colors supplied on each clearing	feature	no	1
magic	enchant chit	feature	no	x
magic	enchant tile	feature	no	x
magic	new game – select starting spells	feature	no	x
magic	setup – initialize magic cards	feature	no	x
magic	show color magic supplied by day on clock	feature	no	x
magic	spells	feature	no	x
map	double-tap on character name centers on character on map	feature	yes	1
map	fix character chit rotation	bug	no	1
map	game piece stack – sort by size	feature	no	1
map	inspect clearing pieces	feature	yes	1
map	make hidden paths brown/green instead of black/yellow	feature	yes	1
map	use pinch zoom to change map size	feature	no	1
monsters	spawn/regenerate ghosts	feature	no	1
natives	hire	feature	no	x
natives	trade	feature	no	x
save/load	basic functionality	feature	yes	1
save/load	multiple save files	feature	no	1
map	if you are in select clearing mode, do not allow changing the activity until a clearing is selected	bug	no	1